# School Climate Action Plan Template

# Contents

Climate Action Plan Template														3-16

Introduction															3

Understanding your current situation in relation to climate action (baseline)					4-5

Decarbonisation															6-7

Biodiversity																8

Adaptation & Resilience														9

Climate Education & Green Careers Goals										10

Other topics															11-16

# Climate Action Plan Template

The table below is a template you can use to complete your climate action plan.

You can include as many goals and actions as like.

As part of the Department for Education’s (DfE) requirements, your plan will need to include at least one action from these four key areas:

- decarbonisation

- biodiversity

- adaptation and resilience

- climate education and green careers goals

The first row has been completed as an example to illustrate an action and the steps that are needed for that goal and you can refer back to our guide for broad ideas of what each topic consists of and how you could take action, the guide also suggests a number of other wider topic areas your school could consider as part of your plan.

You can add as many rows as you like when developing your plan, just right click on the bottom row for each topic area, click insert and then insert rows below.

| Climate Action Area | What am I going to do? (Specific/Action/Plan) | What do I want to achieve by doing this? What is the outcome? (Measurable /Plan) | Do I need any help, support or resources to achieve this? (Achievable /Plan) | Can I do it based on support required? (Realistic /Plan) | When do I want to complete this by? (Time Bound/Plan) |
| --- | --- | --- | --- | --- | --- |
| Understanding your current situation in relation to climate action (baseline) | Find out how much energy my school uses. If on the Council contracts, this can be found by requesting access to Energy Manager – contact the Energy and Environmental Management Team. Otherwise, gather information from invoices over the last 12 months to see how much has been used. From that calculate how much Carbon has been emitted as a result over the last 12 mths. | Once a baseline has been established, a target can be set to reduce emissions over a period of time. | Council support to access data or school finance team. | Yes | March 2026 |
| Understanding your current situation in relation to climate action (baseline) |  |  |  |  |  |
| Decarbonisation | Replace lighting with LED lights: - Undertake audit of current lighting to establish requirement and a business case including potential avenues for funding - Gain approval to move ahead with work/seek funding - Procure a company using correct procurement protocol to undertake the work - Ensure works are suitably project managed - Make required checks on completion. | All lights are switched to LED, reduction in electric use on site, reduction in CO2 emissions | Staff: support from site managers/leadership team/Governors Financial: Funding to implement External: possible support to undertake an audit to produce the business case | If all resources are available - yes | End of Summer 2026 |
| Decarbonisation |  |  |  |  |  |
| Biodiversity | Create a garden for growing things and to learn more about biodiversity. | An outdoor area is created where plants can be grown – increase in plants and wildlife | Staff: support from site managers/leadership team/Governors Financial: Poss small amount of funding to implement or donations | Yes, low cost to no cost and if an area is available for planting | Summer 2026 |
| Adaptation & Resilience | Assess the school risk and vulnerability to climate change – identify risks – you can get Sefton related weather projections here: Explore the Climate of your Local Authority | To identify risks in order to put in place a plan to adapt to potential impacts | Staff: support from site managers/leadership team/Governors Financial: none to create a plan – actions may have a plan. External: may need support to assess and create the plan. | Yes | Summer 2026 |
| Climate Education and Green Careers Goals | Embed sustainability and climate education in the wider curriculum by incorporating it in more lessons. | Increased awareness of pupils of terms and concepts behind sustainability and climate. At least 1 topic covered each term. | Staff: school staff – teachers and head/governor support Finance: could be free | Yes | Summer 2026 |
| Air Quality | Join the Council’s Clean Air Crew resource to educate children on this topic | Empower pupils to understand the issues around air quality and increase alternative methods of getting to school. | Teaching. Access to the resource. | Yes | Summer 2026 |
| Waste | Start to recycle waste | Increase the amount of rubbish being recycled rather than being sent to landfill | Need to source a collection and pay for this. Need financial approval. | If resources in place, yes. | Summer 2026 |
| Water | Undertake a water survey to identify any areas for improvement | To understand where water may be being wasted in order to look at options to remedy this. | May need external support via Council or United Utilities. Actions that form after may need financial support. Could include children/site manager. | Audit should be possible. | Summer 2026. |
| Transport | Hold a walk to school week | Encourage as many people as possible to walk to school rather than using a car. Can monitor how many change habits. | School backing, staffing to supervise arrivals. Parent support. | Yes | During Spring/Summer 2026. |
| Food and Healthy Living | Start a grow your own club | To engage children in learning how to plant and grow simple produce that they can then eat | May need funding for supplies or seek to see if anyone would donate. Area for planting or planters. | If resources in place, yes. | Start by Summer 2026. |
| Global Citizenship | Celebrate Fairtrade Fortnight | Enrich the curriculum for pupils by having them understand principles behind fair pay for a quality product. | Seek resources and help from Fairtrade Foundation | Yes | Sept/Oct 2026 |
| Litter | Undertake litter picking in the local area | Reduce the amount of litter in the local area. | Need equipment such as bin bags, gloves, litter pickers. Risk assessment. Staffing. Support from school leadership. | If resources in place, yes. | Summer 2026 |
| Marine | Make sure pupils use reusable water bottles. | Reduce the use of single use plastics | Could sell school branded water bottles – would need support to buy in first instance or for pupils to bring their own. Support from leadership and parents. | If support is in place, yes. | Summer 2026 |